## Change history
Author | Date | Description | Approved | Approved date
Fitz Nguyen | 2016-04-19 | Initial report | Cang Tran | 2016-04-19
Fitz Nguyen | 2016-04-22 | Update SPI: Add ticket ATFW-199 for SPI, ATFW-200 for I2C | Cang Tran | 2016-04-22

## status
NO. | Module | NO. of TC | Test specification | Test application | Execution | Report | Defects | Fixed | Re-test | Comment
1 | UART | 9 |  |  |  |  | ATFW-109 | ATFW-109
2 | GPIO | 42 |  |  |  |  | ATFW-164, ATFW-188, ATFW-189 | ATFW-164, ATFW-188 |  | ATFW-189 could not be resolve on FPGA_Rev0F
3 | TIMER | 48 |  |  |  |  | ATFW-174 |  |  | Developer confirm that this is HW bug
4 | WDT | 4 |  |  |  |  | ATFW-151, ATFW-165, ATFW-166, ATFW-186, ATFW-187 | ATFW-186, ATFW-151, ATFW-165 |  | - ATFW-187 is not a bug. This issue could not be tested by QC platfrom. - ATFW-166: This is hardware bug. Watchdog timer could not be stopped after started.
5 | PWM | 48 | [5 empty] | ATFW-162 |  | Dev is going to update code base of new FW design of PWM. QC will update test specification. - FW of PWM IRQ is not ready.
6 | I2C | 48 |  |  |  |  | ATFW-161, ATFW-160, ATFW-180, ATFW-181, ATFW-183, ATFW-184, ATFW-200 | ATFW-160, ATFW-161, ATFW-180, ATFW-181, ATFW-183, ATFW-184 |  | ATFW-200 is very high priority. All I2C test cases are failed caused by this defect.
7 | SYNCIO | 32 |  |  |  |  | ATFW-170 |  |  | Bug has not been fixed
8 | SPI | 474 |  |  |  |  | ATFW-175, ATFW-176, ATFW-177, ATFW-178, ATFW-179, ATFW-185 ATFW-199 | ATFW-175, ATFW-176, ATFW-177, ATFW-178, ATFW-179, ATFW-185 |  | Waiting for DMA design to create test scenarios with enable DMA
9 | QSPI | [5 empty] | ATFW-191, ATFW-192, ATFW-193 |  |  | Development team is reworking. Testing is changed to suspended.
10 | DMA
11 | VIC
12 | MIPI
705
Done
On going
Pending
Have not finish implementation
Do not test or implicitly covered
HW bug