## Form
Date | 2016-04-19
Checked | Linh Pham
Confirm | Fitz
Approve | Cang Tran
NO. | Item | Check | Comment
General
1 | Are all input resources provided? - Datasheet - Development source code | YES
2 | Are the verified source code baseline identified? | YES | We have not applied baseline approach
3 | Did you create or update release note?
4 | Did you create or update test user guide?
5 | Did you not the revision of test inputs in release note?
6 | Was release note approved by QC manager and development mamager?
Test Specification
1 | Were all test specification fulfilled?
2 | Were all revision history in test specification, test application updated?
3 | Were all test specification approved?
4 | Were all test report column in test specifications are fulfilled?
5 | Was any failed test case left comment in report and given Bug ticket on Jira?
6 | Did you check spelling in test specification?
Test application
1 | Did you update all revision history in test code (*.h, *.c)?
2 | Did all test code cover all tested module?
3 | Did you check coding standard?
4 | Did you remove redundant test application?
5 | Did you check spelling in test application?
6 | Is there any warning or build error?
7 | Did you re-execute 5 random cases and compare with test result?
Report
1 | Did you fulfill test report (one seperated speadsheet or inside test specification)?
2 | Did you create or update defect report?
3 | Is there any missed defect?
4 | Did all defects have root causes and was confirmed?
5 | Were all defects resolved? Resolving revision (product)?
6 | Is there any Jira ticket that was resolved but it is not marked as "Done"?
7 | Were all Bug ticket linked to main tasks?

## I2C
Date | 2016-04-19
Checked | Hung Bui
Confirm | Fitz
Approve | Cang Tran
NO. | Item | Check | Comment
General
1 | Are all input resources provided? - Datasheet - Development source code | YES
2 | Are the verified source code baseline identified? | YES | We have not applied baseline approach
3 | Did you create or update release note? | YES
4 | Did you create or update test user guide? | YES
5 | Did you not the revision of test inputs in release note? | YES
6 | Was release note approved by QC manager and development mamager? | YES
Test Specification
1 | Were all test specification fulfilled? | YES
2 | Were all revision history in test specification, test application updated? | YES
3 | Were all test specification approved? | YES
4 | Were all test report column in test specifications are fulfilled? | YES
5 | Was any failed test case left comment in report and given Bug ticket on Jira? | NO
6 | Did you check spelling in test specification? | YES
Test application
1 | Did you update all revision history in test code (*.h, *.c)? | YES
2 | Did all test code cover all tested module? | YES
3 | Did you check coding standard? | YES
4 | Did you remove redundant test application? | YES
5 | Did you check spelling in test application? | YES
6 | Is there any warning or build error? | NO
7 | Did you re-execute 5 random cases and compare with test result? | YES
Report
1 | Did you fulfill test report (one seperated speadsheet or inside test specification)? | YES
2 | Did you create or update defect report? | YES
3 | Is there any missed defect? | NO
4 | Did all defects have root causes and was confirmed? | YES
5 | Were all defects resolved? Resolving revision (product)? | NO
6 | Is there any Jira ticket that was resolved but it is not marked as "Done"? | NO
7 | Were all Bug ticket linked to main tasks? | YES

## GPIO
Date | 2016-04-19
Checked | Hung Bui
Confirm | Fitz
Approve | Cang Tran
NO. | Item | Check | Comment
General
1 | Are all input resources provided? - Datasheet - Development source code | YES
2 | Are the verified source code baseline identified? | YES | We have not applied baseline approach
3 | Did you create or update release note? | YES
4 | Did you create or update test user guide? | YES
5 | Did you not the revision of test inputs in release note? | YES
6 | Was release note approved by QC manager and development mamager? | YES
Test Specification
1 | Were all test specification fulfilled? | YES
2 | Were all revision history in test specification, test application updated? | YES
3 | Were all test specification approved? | YES
4 | Were all test report column in test specifications are fulfilled? | YES
5 | Was any failed test case left comment in report and given Bug ticket on Jira? | NO
6 | Did you check spelling in test specification? | YES
Test application
1 | Did you update all revision history in test code (*.h, *.c)? | YES
2 | Did all test code cover all tested module? | YES
3 | Did you check coding standard? | YES
4 | Did you remove redundant test application? | YES
5 | Did you check spelling in test application? | YES
6 | Is there any warning or build error? | NO
7 | Did you re-execute 5 random cases and compare with test result? | YES
Report
1 | Did you fulfill test report (one seperated speadsheet or inside test specification)? | YES
2 | Did you create or update defect report? | YES
3 | Is there any missed defect? | NO
4 | Did all defects have root causes and was confirmed? | YES
5 | Were all defects resolved? Resolving revision (product)? | NO
6 | Is there any Jira ticket that was resolved but it is not marked as "Done"? | NO
7 | Were all Bug ticket linked to main tasks? | YES

## COM
Date | 2016-04-19
Checked | Linh Pham
Confirm | Fitz
Approve | Cang Tran
NO. | Item | Check | Comment
General
1 | Are all input resources provided? - Datasheet - Development source code | YES
2 | Are the verified source code baseline identified? | YES | We have not applied baseline approach
3 | Did you create or update release note? | YES
4 | Did you create or update test user guide? | YES
5 | Did you not the revision of test inputs in release note? | YES
6 | Was release note approved by QC manager and development mamager? | YES
Test Specification
1 | Were all test specification fulfilled? | YES
2 | Were all revision history in test specification, test application updated? | YES
3 | Were all test specification approved? | YES
4 | Were all test report column in test specifications are fulfilled? | YES
5 | Was any failed test case left comment in report and given Bug ticket on Jira? | NO
6 | Did you check spelling in test specification? | YES
Test application
1 | Did you update all revision history in test code (*.h, *.c)? | YES
2 | Did all test code cover all tested module? | YES
3 | Did you check coding standard? | YES
4 | Did you remove redundant test application? | YES
5 | Did you check spelling in test application? | YES
6 | Is there any warning or build error? | NO
7 | Did you re-execute 5 random cases and compare with test result? | YES
Report
1 | Did you fulfill test report (one seperated speadsheet or inside test specification)? | YES
2 | Did you create or update defect report? | YES
3 | Is there any missed defect? | NO
4 | Did all defects have root causes and was confirmed? | YES
5 | Were all defects resolved? Resolving revision (product)? | YES
6 | Is there any Jira ticket that was resolved but it is not marked as "Done"? | YES
7 | Were all Bug ticket linked to main tasks? | YES

## TIMER
Date | 2016-04-19
Checked | Linh Pham
Confirm | Fitz
Approve | Cang Tran
NO. | Item | Check | Comment
General
1 | Are all input resources provided? - Datasheet - Development source code | YES
2 | Are the verified source code baseline identified? | YES | We have not applied baseline approach
3 | Did you create or update release note? | YES
4 | Did you create or update test user guide? | YES
5 | Did you not the revision of test inputs in release note? | YES
6 | Was release note approved by QC manager and development mamager? | YES
Test Specification
1 | Were all test specification fulfilled? | YES
2 | Were all revision history in test specification, test application updated? | YES
3 | Were all test specification approved? | YES
4 | Were all test report column in test specifications are fulfilled? | YES
5 | Was any failed test case left comment in report and given Bug ticket on Jira? | NO
6 | Did you check spelling in test specification? | YES
Test application
1 | Did you update all revision history in test code (*.h, *.c)? | YES
2 | Did all test code cover all tested module? | YES
3 | Did you check coding standard? | YES
4 | Did you remove redundant test application? | YES
5 | Did you check spelling in test application? | YES
6 | Is there any warning or build error? | NO
7 | Did you re-execute 5 random cases and compare with test result? | YES
Report
1 | Did you fulfill test report (one seperated speadsheet or inside test specification)? | YES
2 | Did you create or update defect report? | YES
3 | Is there any missed defect? | NO
4 | Did all defects have root causes and was confirmed? | YES
5 | Were all defects resolved? Resolving revision (product)? | NO
6 | Is there any Jira ticket that was resolved but it is not marked as "Done"? | NO
7 | Were all Bug ticket linked to main tasks? | YES

## PWM
Date | 2016-04-19
Checked | Linh Pham
Confirm | Fitz
Approve | Cang Tran
NO. | Item | Check | Comment
General
1 | Are all input resources provided? - Datasheet - Development source code | YES
2 | Are the verified source code baseline identified? | YES | We have not applied baseline approach
3 | Did you create or update release note? | YES
4 | Did you create or update test user guide? | YES
5 | Did you not the revision of test inputs in release note? | YES
6 | Was release note approved by QC manager and development mamager? | YES
Test Specification
1 | Were all test specification fulfilled? | YES
2 | Were all revision history in test specification, test application updated? | YES
3 | Were all test specification approved? | YES
4 | Were all test report column in test specifications are fulfilled? | YES
5 | Was any failed test case left comment in report and given Bug ticket on Jira? | NO
6 | Did you check spelling in test specification? | YES
Test application
1 | Did you update all revision history in test code (*.h, *.c)? | YES
2 | Did all test code cover all tested module? | YES
3 | Did you check coding standard? | YES
4 | Did you remove redundant test application? | YES
5 | Did you check spelling in test application? | YES
6 | Is there any warning or build error? | NO
7 | Did you re-execute 5 random cases and compare with test result? | YES
Report
1 | Did you fulfill test report (one seperated speadsheet or inside test specification)? | YES
2 | Did you create or update defect report? | YES
3 | Is there any missed defect? | NO
4 | Did all defects have root causes and was confirmed? | YES
5 | Were all defects resolved? Resolving revision (product)? | YES
6 | Is there any Jira ticket that was resolved but it is not marked as "Done"? | NO
7 | Were all Bug ticket linked to main tasks? | YES

## SYNCIO
Date | 2016-04-19
Checked | Linh Pham
Confirm | Fitz
Approve | Cang Tran
NO. | Item | Check | Comment
General
1 | Are all input resources provided? - Datasheet - Development source code | YES
2 | Are the verified source code baseline identified? | YES | We have not applied baseline approach
3 | Did you create or update release note? | YES
4 | Did you create or update test user guide? | YES
5 | Did you not the revision of test inputs in release note? | YES
6 | Was release note approved by QC manager and development mamager? | YES
Test Specification
1 | Were all test specification fulfilled? | YES
2 | Were all revision history in test specification, test application updated? | YES
3 | Were all test specification approved? | YES
4 | Were all test report column in test specifications are fulfilled? | YES
5 | Was any failed test case left comment in report and given Bug ticket on Jira? | NO
6 | Did you check spelling in test specification? | YES
Test application
1 | Did you update all revision history in test code (*.h, *.c)? | YES
2 | Did all test code cover all tested module? | YES
3 | Did you check coding standard? | YES
4 | Did you remove redundant test application? | YES
5 | Did you check spelling in test application? | YES
6 | Is there any warning or build error? | NO
7 | Did you re-execute 5 random cases and compare with test result? | YES
Report
1 | Did you fulfill test report (one seperated speadsheet or inside test specification)? | YES
2 | Did you create or update defect report? | YES
3 | Is there any missed defect? | NO
4 | Did all defects have root causes and was confirmed? | YES
5 | Were all defects resolved? Resolving revision (product)? | YES
6 | Is there any Jira ticket that was resolved but it is not marked as "Done"? | NO
7 | Were all Bug ticket linked to main tasks? | YES

## SPI
Date | 2016-04-19
Checked | Linh Pham
Confirm | Fitz
Approve | Cang Tran
NO. | Item | Check | Comment
General
1 | Are all input resources provided? - Datasheet - Development source code | YES
2 | Are the verified source code baseline identified? | YES | We have not applied baseline approach
3 | Did you create or update release note? | YES
4 | Did you create or update test user guide? | YES
5 | Did you not the revision of test inputs in release note? | YES
6 | Was release note approved by QC manager and development mamager? | YES
Test Specification
1 | Were all test specification fulfilled? | YES
2 | Were all revision history in test specification, test application updated? | YES
3 | Were all test specification approved? | YES
4 | Were all test report column in test specifications are fulfilled? | YES
5 | Was any failed test case left comment in report and given Bug ticket on Jira? | NO
6 | Did you check spelling in test specification? | YES
Test application
1 | Did you update all revision history in test code (*.h, *.c)? | YES
2 | Did all test code cover all tested module? | YES
3 | Did you check coding standard? | YES
4 | Did you remove redundant test application? | YES
5 | Did you check spelling in test application? | YES
6 | Is there any warning or build error? | NO
7 | Did you re-execute 5 random cases and compare with test result? | YES
Report
1 | Did you fulfill test report (one seperated speadsheet or inside test specification)? | YES
2 | Did you create or update defect report? | YES
3 | Is there any missed defect? | NO
4 | Did all defects have root causes and was confirmed? | YES
5 | Were all defects resolved? Resolving revision (product)? | YES
6 | Is there any Jira ticket that was resolved but it is not marked as "Done"? | NO
7 | Were all Bug ticket linked to main tasks? | YES

## WDT
Date | 2016-04-19
Checked | Linh Pham
Confirm | Fitz
Approve | Cang Tran
NO. | Item | Check | Comment
General
1 | Are all input resources provided? - Datasheet - Development source code | YES
2 | Are the verified source code baseline identified? | YES | We have not applied baseline approach
3 | Did you create or update release note? | YES
4 | Did you create or update test user guide? | YES
5 | Did you not the revision of test inputs in release note? | YES
6 | Was release note approved by QC manager and development mamager? | YES
Test Specification
1 | Were all test specification fulfilled? | YES
2 | Were all revision history in test specification, test application updated? | YES
3 | Were all test specification approved? | YES
4 | Were all test report column in test specifications are fulfilled? | YES
5 | Was any failed test case left comment in report and given Bug ticket on Jira? | NO
6 | Did you check spelling in test specification? | YES
Test application
1 | Did you update all revision history in test code (*.h, *.c)? | YES
2 | Did all test code cover all tested module? | YES
3 | Did you check coding standard? | YES
4 | Did you remove redundant test application? | YES
5 | Did you check spelling in test application? | YES
6 | Is there any warning or build error? | NO
7 | Did you re-execute 5 random cases and compare with test result? | YES
Report
1 | Did you fulfill test report (one seperated speadsheet or inside test specification)? | YES
2 | Did you create or update defect report? | YES
3 | Is there any missed defect? | NO
4 | Did all defects have root causes and was confirmed? | YES
5 | Were all defects resolved? Resolving revision (product)? | YES
6 | Is there any Jira ticket that was resolved but it is not marked as "Done"? | NO
7 | Were all Bug ticket linked to main tasks? | YES